## Tasks and Timeline
Artisan Bridge
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Database Design
Discussion of tables models |  |  |  | 1 | team | bar: WEEK 1 M
Normalization of database |  |  |  | 1 | team | bar: WEEK 1 T
Entity relational diagram |  |  |  | 1 | team | bar: WEEK 1 W
Database script MYSQL |  |  |  | 1 | database team | bar: WEEK 1 R
Database implementatation(milestone) |  |  |  | 3 | database team | bar: WEEK 1 F to WEEK 2 T
Backend Routes |  |  |  | 3
Customer routes(milestone) |  |  |  | 1 | bar: WEEK 2 W
login |  |  |  | 1 | backend team | bar: WEEK 2 R
logout |  |  |  | 1 | backend team | bar: WEEK 2 F
register |  |  |  | 1 | backend team | bar: WEEK 3 M
artisans |  |  |  | 1 | backend team | bar: WEEK 3 T
services |  |  |  | 1 | backend team | bar: WEEK 3 F
top rated artisans |  |  |  | 2 | backend team | bar: WEEK 4 T to WEEK 4 W
top rated services |  |  |  | 2 | backend team | bar: WEEK 4 F to WEEK 5 M
Adminstrator routes( milestone) |  |  |  |  | backend team
services |  |  |  | 2 | backend team | bar: WEEK 5 W to WEEK 5 R
update service |  |  |  | 1 | backend team | bar: WEEK 6 T
delete service |  |  |  | 1 | backend team | bar: WEEK 6 T
add service |  |  |  | 1 | backend team | bar: WEEK 6 W
update artisan |  |  |  | 1 | backend team | bar: WEEK 6 R
delete artisan |  |  |  | 2 | backend team | bar: WEEK 7 M to WEEK 7 T
add artisan |  |  |  | 1 | backend team | bar: WEEK 7 R
artisans |  |  |  | 3 | backend team | bar: WEEK 7 F to WEEK 8 T
reports |  |  |  | 1 | backend team | bar: WEEK 8 W
Mockups(milestone) |  |  |  | 16
landing page |  |  |  | 3 | frontend team | bar: WEEK 8 R to WEEK 9 M
login |  |  |  | 1 | frontend team | bar: WEEK 9 T
sign up |  |  |  | 1 | frontend team | bar: WEEK 9 T
adminstrator pages |  |  |  | 2 | frontend team | bar: WEEK 9 T to WEEK 9 W
reports |  |  |  | 1 | frontend team | bar: WEEK 9 W
frontend implementation |  |  |  |  | frontend team
landing page |  |  |  | 3 | frontend team | bar: WEEK 9 W to WEEK 9 F
login |  |  |  | 1 | frontend team | bar: WEEK 9 R
sign up |  |  |  | 1 | frontend team | bar: WEEK 9 R to WEEK 10 T
artisan select |  |  |  | 3 | frontend team | bar: WEEK 9 R to WEEK 10 T
service select |  |  |  | 4 | frontend team
administrator pages |  |  |  | 6 | frontend team | bar: WEEK 10 T to WEEK 10 F
Testing | bar: WEEK 10 F
Backend routes |  |  |  | 1 | backend team | bar: WEEK 10 F
Front end pages |  |  |  | 1 | team | bar: WEEK 10 F
Smoke testing |  |  |  | 1 | team | bar: WEEK 10 F
alpha testing |  |  |  | 1 | team | bar: WEEK 10 F
beta testing |  |  |  | 1 | team | bar: WEEK 10 F
Deployment(milestone) |  |  |  |  | team
Backend server |  |  |  | 2 | Bernard Tawiah | bar: WEEK 11 M to WEEK 11 T
frontend server |  |  |  | 3 | Bernard Tawiah | bar: WEEK 11 T to WEEK 11 R
Database |  |  |  | 2 | Bernard Tawiah | bar: WEEK 11 R to WEEK 11 F
frontend server |  |  |  | 1 | Bernard Tawiah | bar: WEEK 11 F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Database Design (milestone) |  | 7
Discussion of tables models |  | 1
Normalization of database |  | 1
Entity relational diagram |  | 1
Database script MYSQL |  | 1
Database implementatation |  | 1
Backend Routes |  | 3
login |  | 1
logout |  | 1
register |  | 1
artisans |  | 1
services |  | 1
top rated artisans |  | 2
top rated services |  | 2
Adminstrator routes( milestone)
services |  | 1
update service |  | 1
delete service |  | 1
add service |  | 1
update artisan |  | 1
delete artisan |  | 1
add artisan |  | 1
artisans |  | 1
Customer routes(milestone) |  | 1
reports |  | 1
Testing |  | 1
Backend routes
Front end pages |  | 1
Smoke testing |  | 1
alpha testing |  | 1
beta testing |  | 1
Deployment(milestone)
Backend server |  | 2
frontend server |  | 3
Database |  | 2
frontend server |  | 1
Mockups(milestone) |  | 16
landing page |  | 3
login |  | 1
sign up |  | 1
adminstrator pages |  | 2
reports |  | 1
frontend implementation
landing page
login |  | 5
sign up |  | 4
artisan select |  | 3
service select |  | 4
administrator pages |  | 10